## Sheet1
Work Description | Time | Date | Hours
Group's first meeting. Meeting up with the project supervisor and team members to discuss the business opportunity as well as the project's plans and goals. | 12.00-14.00 | 2019-08-12 | 2
Research on how peer to peer applications such as uber and roadie handle insurance and liability issues. | 13.00-18.00 | 2019-08-13 | 5
Reviewing the terms and conditions of peer to peer mobile applications. | 09.30-13.00 | 2019-08-14 | 3.5
Reviewing Roadie application (features, design and how it works). Viewing video tutorials of Roadies as app cannot be used without US phone number. | 13.00-19.00 | 2019-08-17 | 6
Reviewing peer to peer mobile applications - Postmates & DoorDash. | 09.00-13.30 | 2019-08-18 | 4.5
Continue the review of these apps. | 13.30-17.00 | 2019-08-18 | 3.5
Team meeting. | 12.30-14.00 | 2019-08-19 | 1.5
Brainstorming and creating some basic logo design idea sketches for Trippie. | 15.30-18.30 | 2019-08-19 | 3
Final touch-ups on literature review document and uploading it to the shared drive. | 09.00-09.45 | 2019-08-20 | 0.75
Designing a Trippie logo using GIMP and viewing tutorials on how to use GIMP software (used for photo editing and designing logos). | 10.00-16.00 | 2019-08-20 | 6
Team meeting. | 15.30-17.30 | 2019-08-21 | 2
Creating privacy policy document for Trippie application based on previous research while also reviewing privacy policy documents of other applications. | 18.30-22.00 | 2019-08-21 | 3.5
Upload privacy policy document and make additional changes to it. | 10.00-12.30 | 2019-08-22 | 2.5
Re-wording the privacy policy document based on some research and the planning of features going to be added to Trippie and make it sound more professional. | 13.15-16.30 | 2019-08-22 | 3.25
Research on how to model and design NoSQL databases specifically Firebase Cloud Firestore. | 09.30-14.30 | 2019-08-23 | 5
Research on online payment gateways. | 08.30-13.00 | 2019-08-24 | 4.5
Team meeting. | 12.30-14.30 | 2019-08-26 | 2
Research and reading on legal rules and regulations for livestock transportation in New Zealand. | 16.00-19.30 | 2019-08-27 | 3.5
Team meeting. | 15.30-17.30 | 2019-08-28 | 2
Research and comparison of the different payment gateways out there (pricing, integration difficulty, support) | 13.00-18.00 | 2019-08-29 | 5
Reading through the terms and conditions of other peer to peer and ride sharing applications | 18.00-20.30 | 2019-09-30 | 2.5
Viewing tutorials and integrating PayPal payment into a test android app | 9.00-12.00 ¦ 13.00-17.00 | 2019-08-31 | 7
Viewing tutorials and attempting to integrate other payment gateways such as Braintree and Stripe to an android application | 9.00-12.00 ¦ 14.00-19.00 | 2019-09-01 | 8
Creating a comparison table for all the payment gateways based on my research and experimentations. Uploaded the table to the shared drive. | 11.00-12.00 | 2019-09-02 | 1
Team meeting. | 12.45-13.45 | 2019-09-02 | 1
Further research on payment gateways - looking deeper at POLI, eWAY and other NZ based companies. | 15.00-20.00 | 2019-09-03 | 5
Continue reviewing the use cases and documentation provided by the NZ based payment gateways. | 16.00-19.00 | 2019-09-05 | 3
Chatting online with eWAY support on the integration options for Trippie's use case and further research on other payment gateways in NZ. | 12.00-15.30 | 2019-09-06 | 3.5
Viewing tutorials on serverless payment processing in android applications using Firebase and Stripe. Registering an account on Stripe and creating an experimental app than can communicate with the Stripe API. | 10.30-18.30 | 2019-09-07 | 8
Continue working on the experimental app, getting started with cloud functions and studying about idempotent operations. | 9.00-16.30 | 2019-09-08 | 7.5
Team meeting. | 13.00-15.00 | 2019-09-09 | 2
Reviewing chat features of well-known apps like WhatsApp as well the messaging applications on android and IOS as well as the chatting feature in OpenSooq. | 14.30-19.30 | 2019-09-10 | 5
Team meeting. | 15.30-17.00 | 2019-09-11 | 1.5
Viewing tutorials on how to use firebase to build and android chat application. | 9.00-14.30 | 2019-10-12 | 5.5
Viewing tutorials and building a test application that implements the phone authentication functionality provided by firebase. | 11.00-16.30 | 2019-09-13 | 4.5
Complete work on phone auth experiment, experiment with it and upload the app to the shared drive. | 9.00-16.00 | 2019-09-14 | 7
Team meeting at MIT. | 13.30-15.00 | 2019-09-16 | 1.5
Research on database costs for Firebase and ways to keep these costs low. | 10.00-12.00 | 2019-09-17 | 2
Sketching ideas for creating a table for the pricing features and formula. | 12.00-15.30 | 2019-09-17 | 3.5
Team meeting at MIT. | 15.30-17.00 | 2019-09-18 | 1.5
Creating the pricing features table and creating pricing flowcharts based on the table. | 9.00-14.45 | 2019-09-19 | 5.75
Tidy up pricing folder on shared drive and uploaded pricing features table. | 15.00-16.00 | 2019-09-19 | 1
Further reading on Stripe documentation, firebase managing payments use case documentation and watching more tutorials on implementing Stripe payments to an android app. | 11.30-19.30 | 2019-09-20 | 8
Continue the integration of Stripe into an android app and, using cloud functions to register a customer to Stripe and getting back the customer ID generated by Stripe using the Stripe API. | 10.00-16.30 | 2019-09-21 | 6.5
Team meeting. | 13.00-15.00 | 2019-09-23 | 2
Proofreading the wording on all screens in the app, noting down all errors that need to be changed and uploading the changes document to the shared drive. | 12.30-14.00 | 2019-09-24 | 1.5
Team meeting. | 15.30-17.00 | 2019-09-25 | 1.5
Reading and comprehending the code on GitHub for serverless payment systems using firebase. | 9.00-15.30 | 2019-08-26 | 6.5
Working on flowcharts to describe the workflow of the payment module based on prior research. | 9.00-13.45 | 2019-09-28 | 4.75
Continue research on payment and work on the payment module flowcharts. | 11.30-18.00 | 2019-09-29 | 6.5
Proofreading all the flow charts and uploading them to the shared drive. | 11.00-12.15 | 2019-09-30 | 1.25
Team meeting. | 13.00-15.30 | 2019-09-30 | 2.5
Did some more reading on Stripe docs as it seems that we need another way for the payments module in Trippie since we are also paying our service providers through the app itself. | 13.30-18.00 | 2019-10-01 | 4.5
Team meeting. | 15.30-18.00 | 2019-10-02 | 2.5
Working on flowcharts for notifications and offers. | 10.00-16.00 | 2019-10-03 | 6
Uploaded flowcharts to shared drive. Tidied up the folder trees and continued work on the notifications flowcharts. | 09.00-14.30 | 2019-10-04 | 5.5
More research on the options we have in terms of payment gateways that allow us to pay the service providers through the application. | 13.00-20.30 | 2019-10-06 | 7.5
Team meeting. | 12.00-15.00 | 2019-10-07 | 3
Worked on the design of all flow charts to improve consistency and improve readability. | 13.30-16.00 | 2019-10-08 | 2.5
Team meeting. | 15.30-17.30 | 2019-10-09 | 2.5
Reading documents on ways to improve and maintain security of the payment module. | 15.00-19.30 | 2019-10-10 | 4.5
Further research on other payment gateway alternatives to Stripe connect that provide the functionality to pay service providers through the app. | 14.00-19.30 | 2019-10-12 | 5.5
Reading PayPal docs and the PayPal payouts docs to understand the flow of the system and if it is suitable to be used for Trippie. Also, viewing tutorials on apps implementing PayPal and PayPal payouts. | 10.30-18.00 | 2019-10-13 | 7.5
Continue reading on PayPal payouts and how it could be integrated into Trippie. | 11.00-12.30 | 2019-10-14 | 1.5
Team meeting. | 13.00-15.30 | 2019-10-14 | 2.5
Modifying the older flowcharts based on new requirements | 11.00 - 14.00 | 2019-10-15 | 3
Creating flowcharts for the business processes that are missing one. | 15.30-18.00 | 2019-10-15 | 2.5
Working on incident report filing flowchart. | 10.00-13.30 | 2019-10-16 | 3.5
Team meeting. | 15.30-17.30 | 2019-10-16 | 2
Application testing. | 11.00-14.00 | 2019-10-17 | 3
Improving consistency of all flowcharts in terms of design and styling as well as creating the missing ones. | 18.30-21.00 | 2019-10-18 | 2.5
Research on FAQs and reading up the FAQs of Roadie, Uber and other similar apps. | 9.00-12.30 | 2019-10-19 | 3.5
Testing and writing up issues. | 20.00-00.30 | 2019-10-20 | 4.5
Ratings flowchart | 10.30-12.00 | 2019-10-21 | 1.5
Team meeting. | 13.00-15.30 | 2019-10-21 | 2.5
Changes to flowcharts. | 12.00-13.00 | 2019-10-22 | 1
Working on making changes and improvements to the flowchart. | 10.45-14.00 | 2019-10-23 | 3.25
Team meeting. | 14.30-15.30 | 2019-10-23 | 1
Reviewing video tutorials of chat using firebase and getting started on implementing the chat feature on the Trippie app. | 12.00-17.30 | 2019-10-25 | 5.5
Working on designing the UI for chat. | 13.00-20.30 | 2019-10-27 | 7.5
Working on the functionality of chat feature. | 9.00-17.00 | 2019-10-28 | 8
Continue work on chat, doing some testing on multiple phones and fixing some issues. | 12.00-19.30 | 2019-10-29 | 7.5
Designing basic flowcharts for the website after researching on flow charts displayed on other similar websites for example lonelyseat. | 11.00-14.00 | 2019-10-30 | 3
Team meeting. | 14.30-16.30 | 2019-10-30 | 2
Reviewing videos of phone authentication using firebase. | 10.00-14.30 | 2019-10-31 | 4.5
Doing research on the best screen designs for phone authentication screens. | 9.30-15.30 | 2019-11-01 | 6.5
Working on the UI for the phone authentication screens for Trippie and making changes to the existing flow of the login and registration system in the current app version. | 14.00-22.00 | 2019-11-02 | 8
Changes to website flowcharts based on feedback received. | 10.00-11.30 | 2019-11-03 | 1.5
Implementing the phone authentication functionality within the Trippie application, doing some testing and fixing issues. | 13.30-22.00 | 2019-11-03 | 8.5
Working on business processes and how to go about sharing the work and ensuring not more than one person is working on the same business process. | 10.00-11.30 | 2019-11-04 | 1.5
Team meeting. | 13.00-15.00 | 2019-11-04 | 2
Additional flowcharts for the website. | 17.00-19.30 | 2019-11-04 | 2.5
Improvements to website flowcharts. | 9.30-10.30 | 2019-11-05 | 1
Team meeting. | 14.30-16.00 | 2019-11-06 | 1.5
Doing some more testing and improvements on phone authentication | 15.30-19.00 | 2019-11-08 | 3.5
Cancellations flowchart - Tripster's perspective. | 9.00-12.30 | 2019-11-09 | 3.5
Cancellations flowchart - Tripster's perspective (had to redo as I was working based on outdated requirements and specifications) | 12.30-17.00 | 2019-11-09 | 4.5
Testing and writing up issues. | 17.00-20.00 | 2019-11-09 | 3
Research and writing up a report detailing the different Stripe integration options and identifying the best option for Trippie | 10.00-16.00 | 2019-11-10 | 6
Continue testing the app based on the test scripts provided | 16.30-19.30 | 2019-11-10 | 3
Doing some testing based on the testing scripts. | 10.30-12.30 | 2019-11-11 | 2
Team meeting. | 13.00-15.00 | 2019-11-11 | 2
Changes on website flowcharts based on feedback received. | 09.00-10.30 | 2019-11-12 | 1.5
Recording video for Trippie website. | 13.30-17.30 | 2019-11-12 | 4
Installing a video editing software, viewing tutorials on adding transitions to a video and editing yesterday's video recording. | 8.00-14.00 | 2019-11-13 | 6
Team meeting. | 14.30-15.30 | 2019-11-13 | 1
Research and reading on how to make image loading from firebase storage look seamless. | 17.00-21.00 | 2019-11-15 | 4
Viewing tutorials on shared preferences in android studio and using this to save a user's profile image for chat | 9.30-14.00 | 2019-11-16 | 4.5
Using shared preferences to retrieve the image and display it on the screen | 15.00-19.00 | 2019-11-16 | 4
Researching on alternatives to using shared preferences to store images as this is not recommended as well as trying to implement these solutions. | 9.00-12.00 | 2019-11-17 | 3
Implementing a work around using shared preferences as well as fixing some major issues in the chat feature. | 13.00-19.30 | 2019-11-17 | 6.5
Testing the input of all validation fields. | 10.00-12.30 | 2019-11-18 | 2.5
Team meeting. | 13.00-15.00 | 2019-11-18 | 2
Working on the PowerPoint slides for the presentation | 12.30-17.00 | 2019-11-19 | 4.5
Presentation preparation and actual presentation | 10.30-13.30 | 2019-11-20 | 3
Team meeting. | 14.30-15.30 | 2019-11-20 | 1
Research on notification badges and creating a plan of implementing this into the chatting feature in Trippie. | 16.00-18.30 | 2019-11-21 | 2.5
Documenting the workflow of the payments module as well as doing some more reading on Stripe. | 16.30-21.30 | 2019-11-22 | 5
Testing the UI consistency across all screens of the app and writing up the issues in a report. | 15.00-20.30 | 2019-11-23 | 5.5
Research on how to send the input on a WordPress form to the database in Firebase. | 13.30-18.30 | 2019-11-24 | 5
Researching on ways to make improvements to the website as well as reviewing the current design. | 18.30-20.00 | 2019-11-24 | 1.5
Testing and writing up issues. | 9.00-12.00 | 2019-11-25 | 3
Continue testing and noting down issues. | 10.30-12.00 | 2019-11-26 | 1.5
Working on notifications of the chat system in Trippie. Getting familiar with cloud functions to send notifications by viewing tutorials and attempting to implement it in Trippie. | 13.00-18.30 | 2019-11-26 | 5.5
Team meeting. | 14.30-15.30 | 2019-11-27 | 1